# Sample kickoff meeting notes

# Sample kickoff meeting notes

This is a sample document. The organization and people are fictional.

## Meeting details

Organization: Maple Grove Public Library (fictional)

Project: Library website redesign

Date and time: Tuesday, October 13, 2026, 10:00-11:00 AM

Location: Room B

## Attendees

| Name | Role |
| --- | --- |
| Dana Ortiz | Library Director, sponsor |
| Sam Lee | IT Lead |
| Priya Nair | Youth Services |
| Tom Becker | Communications |
| Alex Kim | Web contractor |

## Goals

Patrons can renew books and place holds from a phone in under a minute.

Event calendar is updated by staff without IT help.

Site meets WCAG 2.2 AA.

## Timeline

| Phase | Dates |
| --- | --- |
| Discovery | October 13-30, 2026 |
| Design | November 2-20, 2026 |
| Build | November 23, 2026-January 15, 2027 |
| Staff training | January 18-22, 2027 |
| Launch | January 25, 2027 |

## Decisions

Alex Kim will run three patron interviews per age group: teens, adults, and seniors.

Tom Becker owns all site copy.

Weekly check-ins will take place on Tuesdays at 10:00 AM.

## Risks

| Risk | Owner |
| --- | --- |
| Holiday staff availability in December | Dana Ortiz |
| Catalog vendor API access not yet confirmed | Sam Lee |

## Action items

| Action item | Owner | Due date |
| --- | --- | --- |
| Request catalog vendor API docs | Sam Lee | October 16, 2026 |
| List top 10 youth program pages | Priya Nair | October 20, 2026 |
| Collect current site analytics | Tom Becker | October 20, 2026 |
| Draft interview plan | Alex Kim | October 19, 2026 |
| Confirm December staff schedule | Dana Ortiz | October 27, 2026 |

## Additional notes

Budget: $18,000 approved by the library board for phase 1.

Out of scope for phase 1: Catalog system replacement; online payments.

Next meeting: Tuesday, October 20, 2026, 10:00 AM.